## Sheet1
| Project #: | 162-83 |  |  |  | Design & Construction
| Title: | Harder Stadium CCBER Photovoltaic Project - Phase II |  |  |  | FORECAST
| Project Manager: | George Levinthal |  |  |  | WORKORDER PROJECT
| Date of last Workorder Report: | 02.20.11 |  |  | As of: | 02.20.11
Date of last Forecast Review:
Figures from LAST WO Report:
TGIF Grant Funding
Less: Expended to Date:
Less: Cont/Auth/PO Lien Balances
Current WO Budget Balance: |  |  | 1 | 5 | 6 | 7 | 8 | 9 | 3
|  |  | Construction | External Fees | Internal Fees | Tests Plans Spec | Special Items | Contingency | Equipment
FORECASTED to complete: |  | Category totals:
(Items NOT yet Formalized)
Blum/REC Solar Elect. Estimate |  | 40090 | 40090
2% Bond (Included) |  | 0
Roof Flashing (included)
Asbestos/Lead Paint Testing & Abatement Allowance |  | 0 | 0
Builders Risk Insurance |  | 0
CommServices Allowance |  | 0
Air/Water Balance |  | 0 | 0
MetaSys |  | 0
ReKey |  | 0
Shop Labor |  | 500 | 500
CSO Security |  | 0 | 0
Construction signs |  | 0
Offsite Mitigation |  | 0 | 0
Temporary Utilities |  | 0 | 0
0
Engineer's Basic Services |  | 0
Arch.Special Consultants |  | 0 |  | 0
Arch.Reimbursables |  | 0 |  | 0
Arch.Extra Services |  | 0
Arch.Const. Services |  | 0 |  | 0
Printing/Shipping |  | 250 |  |  |  | 250
Advertising |  | 0 |  |  |  | 0
Travel |  | 0 |  |  |  | 0
Supplies |  | 0 |  |  |  | 0
Phones/Equipment |  | 0 |  |  |  | 0
Soils investigation |  | 0 |  |  |  | 0
Surveying |  | 0 |  |  |  | 0
Soils Tests |  | 0 |  |  |  | 0
Project Manager@$95/hr(x32hours) |  | 3040 |  |  | 3040
Principal @$139/hr |  | 0
Admin Assistance @$43/hr |  | 0
Inspector @$71/hr (x16hours) |  | 1136 |  |  | 1136
Office of State Architect (OSA) |  | 0 |  |  |  |  | 0
SFM |  | 0 |  |  |  |  | 0
Surge Space |  | 0 |  |  |  |  | 0
Peer Electrical |  | 0
Peer Structural |  | 0
Peer MEP |  | 0 |  |  |  |  | 0
CCR |  | 0 |  |  |  |  | 0
Roofing Consultant |  | 0
Scheduling Consultant |  | 0 |  |  |  |  | 0
Constructability |  | 0 |  |  |  |  | 0
Campus Model/Atlas |  | 0 |  |  |  |  | 0
Design Review |  | 0 |  |  |  |  | 0
0
Contingency (10%) |  | 4009 | [5 empty] | 4009
Total Forecasted Items: |  | 49025 | 40590 | 0 | 4176 | 250 | 0 | 4009 | 0
Liened, Expended & Forecasted: |  | 49025 |  | NOTE: IF YOU CHOOSE OPTION #1 IN BLUM'S PROPOSAL, THE TOTAL COSTS WEOULD BE $44,537.00
Forecasted WO Project Balance: |  | -49025